## function_point
Function Point Computation

		Weighting Factor
Measurement Parameter	Count	Simple	Average	Complex
Inputs	24	4	4	6	96
Outputs	16	5	5	7	80
User Inquiries	22	4	4	6	88
Number of Files	4	10	10	5	40
Number of External interfaces	2	7	7	10	14
				Total	318	*uses simple weighting factor

Complexity Adjustment Values				Rate
1. Does the system require reliable backup and recovery?				4		0-No influence
2. Are data communications required?				2		1-Incidental
3. Are there distributed processing functions?				0		2-Moderate
4. Is performance critical?				4		3-Average
5. Will the system run in an existing operational environment?				3		4-Significant
6. Does the system require on-line data entry?				4		5-Essential
7. On-line data entry to be built over multiple screens?				5
8. Are the master files updated on-line?				3
9. Are the inputs, outputs, files complex?				5
10. Is the internal processing complex?				5
11. Is the code designed to be reusable?				4
12. Are conversion and installation included in the design?				3
13. Is the system designed for multiple installations?				5
14. is the application designed to facilitate change?				5
			Total	52

Function Point	372.06
Effort(pm) for Function Point	6.5	*based on historical data
Programmer Salary Per Month(PHP)	15000	*starting
Cost per FP (PHP)	2307.69