CMSC 128
Introduction to Software Engineering
Second Semester AY 2007-2008
jachermocilla@uplb.edu.ph

---
Software Project Planning
Project planning marks the start of the project management process
Estimation is the first activity in project planning
When estimates are made, we look into the future and accept some degree of uncertainty
Estimation is both science and art
  - Need not be conducted haphazardly

---
Software Project Planning
What to estimate?
  - resources, cost, and schedule
Factors affecting estimation
  - Project complexity
  - Project size
  - Structural uncertainty
  - Availability of historical data

---
Software Project Planning
Objective
  - Provide a framework that enables the manager to make reasonable estimates of resources, cost, and schedule within a limited time frame at the beginning of the project.
  - Define best-case and worst-case scenarios so that outcomes can be bounded

---
Software Scope
Function and performance allocated to software during system engineering must be assessed to establish a project scope
Software scope describes function, performance, constraints, interfaces, and reliability
Software scope must be unambiguous and understandable at management and technical levels

---
    Obtaining Info for Scope
Must communicate with customer
First set of context-free questions
  - Who is behind the request for this work?
  - Who will use the solution?
  - What will be the economic benefit of a successful solution?
  - Is there another source for the solution?

---
    Obtaining Info for Scope
Second set of context-free questions
  - How would you characterize good output of the successful solution?
  - What problems will this solution address?
  - Can you show me the environment in which the solution will be used?
  - Are there special performance issues that will affect the way solution is approached?

---
    Obtaining Info for Scope
Third set of context-free questions
  - Are your answers official?
  - Are my questions relevant to the problem that you have?
  - Am I asking too many questions?
  - Is there anyone else who can provide additional information?
  - Is there anything else that I should be asking you?

---
Resources
After defining the scope, resources must be estimated
Each resource is characterized by
  - Description
  - Statement of availability
  - Chronological time that the resource will be required
  - Duration of time that the resource will be applied

---
Resources

---
Resources
Human Resources
  - Skills required are identified
  - Both organizational(ex. manager) and specialty(ex. DBA) positions are specified
Reusable Resources
  - Off-the-shelf components
  - Full-experience components
  - Partial-experience components
  - New components

---
Resources
Environmental Resources
  - Supports the project: both hardware and software
  - Software Engineering Environment
  - Development Environment

---
Estimation
Options to obtain reliable estimates
  - Delay estimation until late in the project
  - Base estimates on similar projects that have already been completed
  - Use decomposition techniques
  - Use one or more empirical models for software cost and effort estimation

---
Decomposition
Can use problem or process decomposition
Understand the scope and generate an estimate of 'size'

---
Software Sizing
Factors affecting project estimates
  - Estimate of the size of product
  - Ability to translate size estimate into effort, time, and cost
  - Degree to which project plan reflects the ability of the team
  - Stability of requirements and SEE
In project planning, size refers to the quantifiable outcome of the software project (LOC or FP)

---
Software Sizing
Approaches
  - 'Fuzzy-logic' sizing
  - Function point Sizing
  - Standard component sizing
    - Some software have 'standard components'
      - Modules, reports, screens, etc
  - Change sizing
    - When using existing software that must be modified
    - Estimates the number and type of modifications(adding, deleting, reuse, etc.)

---
     Problem-based Estimation
Use of LOC and FP in estimation
  - Estimation variable that is used to 'size' each element of software
  - Baseline metrics collected from past projects and used together with estimation variables to develop cost and effort projections
Planner begins with bounded statement of software scope, then decompose software into problem functions that can each be estimated individually using LOC or FP

---
     Problem-based Estimation
Baseline productivity metrics (LOC/pm or FP/pm) are applied to the estimation variable and cost or effort for the function is derived
In using LOC as estimation variable, decomposition is essential to obtain more accurate estimates
In using FP as estimation variable, countable information domain and complexity adjustment values are used

---
     Problem-based Estimation
When estimating (based on historical data or intuition), specify optimistic, pessimistic, and most likely size
Three point value or expected value is computed
  - EV = (opt + 4*most_likely + pess)/6

---
     Process-based Estimation
Identify framework activities and tasks for the selected process then estimate the effort required for each
  - Unit of effort is person-month, the amount of work that a person can do in one month
Decompose software into problem functions
Meld the product and the process

---
Empirical Models
Use empirically derived formulas to predict effort as a function of LOC or FP
General structure
  - Effort = A + B x (estimation var)C , where A, B, and C are empirically derived constants
Examples
  - Walston-Felix, E=5.2 x KLOC0.91
  - Bailey-Basili, E=5.5 x 0.73 x KLOC1.16

---
COCOMO
COnstructive COst MOdel, by Boehm
Hierarchy of models
  - Model 1 - basic
    - Effort(and cost) as function of size (LOC)
  - Model 2 - intermediate
    - Same as Model 1 but includes 'cost drivers'
  - Model 3 – advanced
    - Same as Model 2 but includes assessment of cost drivers impact on each step

---
COCOMO
Three classes of software projects
  - Organic
    - Relatively small, small teams, less rigid requirements
  - Semi-detached
    - Intermediate in size and complexity
    - Teams with mixed experience
  - Embedded
    - Tight constraints

---
COCOMO
Basic
  - E=a*KLOCb, D=c*Ed
Semi-detached
  - E=a*KLOCb x Effort_Adjustment_Factor

---
Summary

---
Reference
Roger S. Pressman.Software Engineering: A Practitioner's Approach, 4th Ed.McGraw-Hill,1997. Chapter 5