## LOC
LOC Based

Function/Module	Optimistic (1)	Most Likely(4)	Pessimistic(1)	Estimated/Expected LOC
User Interface				2300
2D Geometric Analysis				5300
3D Geometric Analysis	4600	6900	8600	6800
Database Management				3350
Graphics and Display				4950
Peripheral Control				2100
Design Analysis				8400
			Total	33200

Productivity(LOC/pm)	620	*based on historical data on similar project
Salary (PHP)	15000
Cost per LOC (PHP)	24.19

Project Cost (PHP)	803225.81
Effort (person-month)	53.55

## function_point
Function Point Computation

		Weighting Factor
Measurement Parameter	Count	Simple	Average	Complex
Inputs	24	4	4	6	96
Outputs	16	5	5	7	80
User Inquiries	22	4	4	6	88
Number of Files	4	10	10	5	40
Number of External interfaces	2	7	7	10	14
				Total	318	*uses simple weighting factor only

Complexity Adjustment Values				Rate
1. Does the system require reliable backup and recovery?				4		0-No influence
2. Are data communications required?				2		1-Incidental
3. Are there distributed processing functions?				0		2-Moderate
4. Is performance critical?				4		3-Average
5. Will the system run in an existing operational environment?				3		4-Significant
6. Does the system require on-line data entry?				4		5-Essential
7. On-line data entry to be built over multiple screens?				5
8. Are the master files updated on-line?				3
9. Are the inputs, outputs, files complex?				5
10. Is the internal processing complex?				5
11. Is the code designed to be reusable?				4
12. Are conversion and installation included in the design?				3
13. Is the system designed for multiple installations?				5
14. is the application designed to facilitate change?				5
			Total	52

Function Point	372.06
Effort(pm) for Function Point	6.5	*based on historical data on similar project
Programmer Salary Per Month(PHP)	15000	*starting
Cost per FP (PHP)	2307.69

Project Cost (PHP)	858600
Effort (person-month)	57.24

## process_based
Activity		Customer	Planning	Risk	Engineering		Construction		Customer
		Communication		Analysis			Release		Evaluation	Totals

Task					Analysis	Design	Code	Test

Function

User Interface					0.50	2.50	0.40	5.00		8.40
2D Geometric Analysis					0.75	4.00	0.60	2.00		7.35
3D Geometric Analysis					0.50	4.00	1.00	3.00		8.50
Database Management					0.50	3.00	1.00	1.50		6.00
Graphics and Display					0.50	3.00	0.75	1.50		5.75
Peripheral Control					0.25	2.00	0.50	1.50		4.25
Design Analysis					0.50	2.00	0.50	2.00		5.00

Total		0.25	0.25	0.25	3.50	20.50	4.75	16.50		46.00

%Effort		1%	1%	1%	8%	45%	10%	36%

Programmer Salary Per Month(PHP)	15000	*starting

Project Cost (PHP)	690000
Effort (person-month)	46

## COCOMO
COCOMO

Basic Model	a	b	c	d		Intermediate Model	a	b
Organic	2.4	1.05	2.5	0.38			3.2	1.05
Semi-detached	3	1.12	2.5	0.35			3	1.12
Embedded	3.6	1.2	2.5	0.32			2.8	1.2

Effort	94.93
Duration	14.1
People Needed	6.73