CMSC 128
Introduction to Software Engineering
Second Semester AY 2007-2008
jachermocilla@uplb.edu.ph

---
     Scheduling and Tracking
Why is software delivered late?
  - Unrealistic deadline established by someone outside the SE group
  - Changes in requirements not reflected in schedule
  - Honest underestimate of effort and resources
  - Risks not considered when project started
  - Technical and human difficulties
  - Miscommunication
  - Failure to recognize and act on possible delay

---
Basic Principles
How do projects fall behind schedule?
  - 'One day at a time.' --F Brooks
In a project, a set of small tasks must be performed to accomplish a goal
  - Some of these tasks are 'critical' and may affect schedule
Define all tasks, identify the critical tasks, track the progress of the critical tasks

---
Basic Principles
Scheduling
  - Distributes estimated effort across the planned project duration by allocating the effort to specific software engineering tasks
  - Schedules evolves over time
  - From macroscopic (framework activities) to microscopic (tasks)
  - First view: End date for release is set
  - Second view: End date is set by SE organization

---
Basic Principles
Compartmentalization
  - Product and process decomposition
Interdependency
  - Some tasks must occur in sequence, others in parallel
Time allocation
  - Each task must be allocated some work units
  - Start and completion date are functions of interdependency

---
Basic Principles
Effort Validation
  - With a defined number of staff, no more than the allocated staff should have been allocated at a given time
Defined responsibilities
  - Every task scheduled must be assigned to a specific team member
Defined outcomes
  - Deliverables(work product) are produced

---
Basic Principles
Defined milestones
  - Task or group of tasks is associated with a project milestone
  - A milestone is accomplished when one or more work products have been reviewed for quality and have been approved

---
People and Effort
In a small project, a single person can do everything: analysis, design, code, test, etc.
Big projects require more people
So, if project is behind schedule, perhaps the project is big! Add more people??
  - Consider communication and training

---
People and Effort
Consider four developers individually capable of producing 5K LOC/yr
Produce a team from these developers, there will be six communication paths, assume that productivity will be reduced by 250 LOC/yr.
What will be the productivity of each developer now?
Imagine if we add two more developers because project is behind schedule!

---
People and Effort
Relationship between people and productivity is not linear
Can we conclude then that forming teams is counterproductive?
  - NO!
  - If communication serves to improve quality: formal technical reviews
Benefit can be gained by using fewer people over a somewhat longer time span

---
Effort Distribution
Estimation produces estimate of effort
40-20-40 rule
Characteristics of project dictate the distribution of effort
  - Project planning – 2-3 percent
  - Requirements Analysis – 10–25 percent
  - Software Design – 20-25 percent
  - Coding – 15-20 percent
  - Testing – 30-40 percent

---
Defining Task Sets
At the start of the project, a software process model is selected
Process model selected consists of task sets (applies to any software process model)
Task sets vary depending on the project
A task set is a collection of software engineering work taks, milestones, and deliverables that must be accomplished to complete a project

---
Defining Task Sets
Task set should provide enough discipline to achieve quality and not burden the team with unnecessary work
Task sets are designed to accommodate different types of projects and different degrees of rigor

---
Types of Projects
Concept Development
  - Explore some new concept, apply new tech
New Application Development
  - From customer request
Application Enhancement
  - Modifications obervable by the end user
Application Maintenance
  - Modifications not obvious to end user
Reengineering - rebuilding

---
Degree of Rigor
Casual
  - All framework activites are applied but with only a minimum task set: umbrella activities are minimized documentation requirements are reduced
Structured
  - All framework activities are applied, including all umbrella activities
Strict
  - Same as structured but robust documentation

---
Degree of Rigor
Quick Reaction
  - Framework activities are applied, but because of emergency situations, only essential activities will be applied
  - 'Back-filling','to follow'

---
Adaptation Criteria
Selecting the degree of rigor must be systematic, based on some criteria
Adaptation Criteria: size of project, number of potential users, mission criticality, application longevity, stability of rquirements, ease of developer/customer communication,maturity of applicable technology,performance constraints, embedded characteristics, staffing, reengineering

---
Selecting SE Tasks
Developing project schedule requires the task set to be distributed on the project timeline
Task set vary depending on the project type and degree of rigor
One type of project may flow smoothly to the next: from concept to new application

---
Concept Development
Major Tasks (macroscopic)
  - Concept scoping
  - Concept planning
  - Technology risk assessment
  - Proof of concept
  - Concept implementation
  - Customer reaction to concept
Major tasks refined through decomposition to create final schedule

---
Task Networks
Tasks and subtasks have interdependencies based on their sequence
Some tasks can be performed in parallel
Task network is a graphical representation of task flow
Determine tasks that lie on the critical path
  - Tasks that determine overall schedule

---
Scheduling
Program Evaluation and Review Technique (PERT) and Critical Path Method (CPM)
  - Requires
    - Estimates of effort
    - Decomposition of product function
    - Selection of process model
    - Selection of project type and task set
Work Breakdown Structure (WBS) – task decomposition as task network

---
Scheduling
What can PERT/CPM do?
  - Determine critical path
    - Chain of tasks that determine the duration
  - Establish most likely time estimates for individual tasks
  - Calculate boundary times
    - Earliest time to start
    - Latest time to start
    - Earliest finish
    - Latest finish
    - Float time (leeway)

---
Gantt Charts
WBS is created and entered in an automated scheduling tool
For each task: effort, duration, start date, and human resource are specified
Created for entire project or portions of it
Example tools: MS Project, Imendio/Planner (linux)

---
Project Tracking
Project schedule provides roadmap
How to track?
  - Periodic project status meeting
  - Evaluate results of all reviews
  - Determine if milestones have been achieved
  - Compare actual start date to planned start date
  - Informal meeting with practitioners to obtain subjective assessment of progress

---
Control
Employed to administer project resources, cope with problems, and direct project staff
Project is going well, light control
When problems occur
  - Allocate resource
  - Redeploy staff
  - Redefine Schedule

---
Control
Deadline pressures??!!!
Time-boxing
  - Complete product may not be delivered on time
  - Incremental approach is selected
  - Schedule of tasks associated with increment is adjusted backwards from deadline of increment
  - When task hits boundary, work stops and next task begins

---
Summary
Scheduling is the culmination of planning activity
Scheduling starts with process decomposition
Task set is adapted based on type and degree of rigor
Scheduling tools include PERT, CPM, Gantt Chart, Project Table
Schedule used to track and control project

---
Reference
Roger S. Pressman.Software Engineering: A Practitioner's Approach, 4th Ed.McGraw-Hill,1997. Chapter 5